Section 9: Proposal Phase Execution

Subsection: Proposal Kickoff & Brief

## 1. Title

Proposal Kickoff & Brief

## 2. Purpose

To formally initiate the proposal development phase by aligning all stakeholders on the opportunity, schedule, expectations, and content responsibilities. The kickoff brief ensures unified understanding of customer requirements and supports efficient execution under tight timelines.

## 3. Scope

Applies to all proposals that have received Gate 3 approval and are entering the active writing and submission phase. Includes all Albers BD, Capture, Proposal, and Program personnel involved in proposal delivery.

## 4. Principles & Guardrails

- Kickoffs are required for all RFPs and DRFPs proceeding to full proposal.

- Kickoffs must be held within 2 business days of Gate 3 approval.

- Focus is on enabling execution, not duplicating capture discussions.

- Proposal Managers may tailor the briefing depth based on complexity, size, and team familiarity.

- Content leads should walk away with clarity on: what they owe, when it’s due, and how it aligns with the customer’s evaluation criteria.

## 5. Key Roles

- Proposal Manager (Ryan Flood): Owns kickoff scheduling, agenda, brief content, and follow-up.

- Capture Manager: Provides technical strategy, past performance alignment, and customer context.

- Volume Leads: Confirm authorship responsibilities and timelines for Technical, Management, Past Performance, and Pricing sections.

- Contracts/Pricing: Confirm assumptions, pricing inputs, and schedule alignment.

- BD Ops (Greg James): Supports GovDash alignment and initial compliance matrices.

- Salesforce/CRM (Renee Mittenmeyer): Ensures opportunity snapshot is current and triaged correctly.

## 6. System Touchpoints

- Salesforce: Opportunity data must be accurate and current before kickoff.

- GovDash: Used to store the kickoff brief, schedule, color team dates, and final artifacts.

- ClickUp: Task assignments for volume leads and delivery tracking.

## 7. Compliance Markers

None required. This is an internal execution milestone. However, the kickoff sets the foundation for compliance with FAR 52.215-1 (Instructions to Offerors) and must account for all submission requirements, page limits, formatting, and required volumes.

## 8. Optional Tools or Templates

- Albers Proposal Kickoff Brief Template (PPTX or PDF)

- GovDash Color Review Tracker

- Content Tracker or Authoring Template

## 9. Review & Update Cycle

- Owned by Ryan Flood (Proposal Manager)

- Reviewed semi-annually in coordination with BD Ops (Greg James) and CRM Lead (Renee Mittenmeyer) for alignment to evolving systems and team feedback.