SOP: B&P Management

1. Title
B&P (Bid & Proposal) Management – Resourcing, Tracking, and Accountability

2. Purpose
To define how Capture Managers plan, request, and manage Bid & Proposal (B&P) resources. Proper B&P discipline ensures proposals are supported by the right people, within budget, and tracked accurately through Salesforce.

3. Scope
Applies to all Capture Managers, Program Managers, Proposal Managers, Finance, and VPs providing staff support for proposal efforts. Governs planning, authorization, charge codes, and tracking of B&P resources.

4. Intent

- Building the Proposal Team

  - Capture Manager identifies proposal support needs (e.g., writers, SMEs, contracts, pricing, HR).

  - Requests resources from the appropriate VP if the support involves that VP’s direct-charge employees.

  - Salaried employees (not direct-charge) do not require B&P codes for support.

- Hours & Costing

  - Capture Manager estimates required hours for each teammate.

  - Finance prices the support plan and confirms estimated B&P budget.

  - All assumptions must be realistic, executable, and tied to the PWin assessment.

- Charge Codes

  - A unique B&P charge code must be established for each pursuit requiring direct-charge support.

  - Every charge code must include a start date and an end date.

  - End date = Proposal Submission + 3 months (to cover slips, extensions, clarifications).

  - Direct-charge employees record proposal hours to this code.

  - Capture Manager monitors hours charged against the approved budget.

- Tracking & Accountability

  - Salesforce is the system of record for all B&P activity.

  - Salesforce includes a B&P Estimator tool to provide estimated B&P costs based on predefined criteria.

  - Estimator outputs are only a planning aid — Capture Managers must still track actual B&P spend to avoid overruns.

  - B&P must be closely managed to ensure annual B&P allocations, overseen by the VP of BD, are not exceeded.

  - Actual B&P executed during the year is documented and used as the baseline for next year’s BD B&P budget request.

- Leadership Oversight

  - VPs authorize use of their employees.

  - Finance validates cost realism.

  - VP of BD manages total B&P allocation across the company.

  - Capture Manager is accountable for staying within approved budget.

✅ Bottom Line: B&P is a limited corporate resource. Capture Managers must plan early, use Salesforce tools for estimates, assign charge codes with start/end dates, and tightly manage execution in Salesforce. Annual B&P spend rolls into next year’s request — discipline today protects resources tomorrow.